| Meeting purpose: | Ping! Exeter Steering Group |
| --- | --- |
| Date: | Monday 18th May 2015 |
| Time: | 14.00-16.00 |
| Location: | Exeter City Football Club, Stadium Way, Exeter EX4 6PX |
| Attendees: | James Bogue, Katy Leonard, Chris Brown, Scott Walker, Jamie Vittles, Penny Perry, Paul Mouland |
| Apologies: | Dan Pulsford, David Conn, Steve Derbyshire |

AGENDA

| Item No. | Time Allocated | Item | Lead | Actions |
| --- | --- | --- | --- | --- |
| GENERAL |  |  |  |  |
| 1. | 5 | Welcome and Introductions | JB |  |
| 2. | 15 | Table Tennis England Update LOOP – website now live http://tabletennisengland.co.uk/loop/ Offers include workplaces, Clubhouses, Bar/Café, Campus (University/Colleges). The offers include a subsided discount of table tennis resources. Year 2 Priority Zone strategy – South West is Southampton, Bournemouth and Exeter. Targets – New participants and facilities, disability specific pot of funding. | CB | Action 1 – CB/KL set up meeting with the Cavern to use as a pilot for the Bar/Café offer |
| 3. | 30 | Ping Event Planning Volunteer Workshop – Monday 8th June 5.30-6.45pm at ECFC run by CB. Launch – Friday 19th June 11am-4pm | JB / KL | Action 2 – KL to organise matches between local businesses i.e. Radio Exe vs E&E for Launch, speak to Princesshay about music. |
| 4. | 30 | Legacy project update |  |  |
|  |  | ECFC Satellite club running, tournament running between the satellite clubs on 30th June 4pm – 6pm at St Lukes School. Looking to organise a young leader’s course. Half term holiday club 12-3pm on Tues 26th May at ECFC. | JV |  |
|  |  | EDTTL Looking to expand junior league, suggested 2 age groups. Wednesday 3rd June is the next ETTL meeting at 7.30pm. Look to have a list of clubs on the Ping tables. Finals competition held in Plymouth. | PP |  |
|  |  | Exeter College Hopeful of resubmitting the Sport England Smalls Grants by the end of the next week. | DP |  |
|  |  | University of Exeter Pongathon 30 new people, with 10-20 people attending regularly per week. Looking to get Ping Packs in halls of residence. CB suggested the Loop Campus offer for the University. Committee are running Pongathon next academic year rather than PM. | PM |  |
| 5. | 15 | Workplace Activity Working on a workplace website with Big Wave Media to create an online social league so workplaces can organise matches between eachother, log the results linked with social media. | JB | Action 3 – JB/KL to set up meeting with Debbi Moore from Big Wave Media |
| 6. | 10 | AOB Ping Finale event will now take place at Exeter City FC on Wednesday 9th September rather than Exeter Castle. Times TBC | ALL |  |
|  |  | Next meeting: Monday 17th August 2pm – 4pm at ECFC |  |  |